Homework 1

- Research

- What already exists that is like our application?

There are already existing popular music streaming applications such as Spotify, Apple Music, and YouTube Music. These applications and others like them have a very distinct goal in mind, which is to listen to songs, create playlists and receive personalized recommendations.

- What makes our application different?

Unlike traditional music streaming applications, our application focuses on user-controlled music discovery. The recommendation system will adapt to changes in a user's musical taste while allowing the user to determine how familiar, diverse, or obscure their recommendations should be. Rather than continuously recommending music similar to what the user already listens to, the system will gradually introduce new artists, genres, and sounds that expand the user's musical interests while remaining relevant to their existing preferences.

- Vision and Scope

- Who are we and how was this project acquired?

We are Evolve Music Technologies, a software company focused on creating a better way for people to listen to and discover music. Our goal is to create a music streaming application that feels more personalized to each user and changes along with their music taste.

The Evolve project started after we noticed that recommendations on current  streaming platforms can become repetitive and do not always change as a 	 music taste changes. We decided to develop our own music streaming application that gives users more control over their recommendations. Evolve will help users find new artists and genres that are different enough to expand their music taste while still being similar to the music they already enjoy.

b. What is the vision of the project?

The vision of Evolve is to create a music streaming application that makes discovering new music more personalized to each user. Instead of only recommending songs that are very similar to what someone already listens to, Evolve will help users branch out into new artists, sounds, and genres while still keeping recommendations related to their current music taste.

We also want users to have more control over their recommendations. Since people's music tastes can change over time, Evolve will adjust its recommendations based on both recent and previous listening habits. Users will also be able to influence how much variety they want in their recommendations, allowing them to choose between music that is more familiar or music that helps them explore something new.

- What is the scope of the project?

The scope of Evolve will include the main features expected from a music streaming application, such as creating an account, searching for songs and artists, listening to music, creating and managing playlists, liking songs, and viewing listening history.

The main focus of the project will be Evolve's personalized recommendation and discovery system. Users will receive recommendations based on their listening habits and will be able to give feedback to improve future recommendations. Users will also have control over how adventurous their recommendations are and whether they want to discover more popular or lesser-known artists.

For the first version of Evolve, features such as podcasts, audiobooks, merchandise, concert ticket sales, and live radio will not be included. This will allow the project to focus primarily on music streaming and personalized music discovery.

- Draft for SRS

      - Create Account — The user can create an Evolve account.

      - Log In — The user can log into an existing account.

      - Search Music — The user can search for songs, albums, and artists.

      - Play Music — The user can select and play a song.

      - Create Playlist — The user can create their own playlists.

      - Manage Playlist — The user can add or remove songs from a playlist.

      - Like Songs — The user can like songs to help build their music profile.

      - View Listening History — The user can see songs they previously listened to.

      - Receive Personalized Recommendations — The system recommends music based on the user's listening habits.

      - Adjust Discovery Level — The user can choose between more familiar or more adventurous recommendations.

      - Adjust Artist Popularity — The user can choose whether recommendations favor popular or lesser-known artists.

      - Give Recommendation Feedback — The user can tell the system whether they want more or fewer recommendations similar to a particular song.

      - View Recommendation Explanation — The user can see why a song or artist was recommended.

      - Follow Artists — The user can follow artists they are interested in.

      - View Artist Profile — The user can view an artist's songs, albums, and other information.

Homework 2

- Create WBS for App

-1.0 Music Recommendation Application

-1.1 Project Planning

- 1.1.1 Define project vision and scope

- 1.1.2 Identify stakeholders

- 1.1.3 Define project requirements

- 1.1.4 Create project schedule

-1.2 UI/UX Design

- 1.2.1 Design login/signup screens

- 1.2.2 Design home/dashboard

- 1.2.3 Design music discovery interface

- 1.2.4 Design user profile and settings

-1.3 User Account System

- 1.3.1 Implement account registration

- 1.3.2 Implement login/logout

- 1.3.3 Store user preferences

- 1.3.4 Manage favorite artists and songs

-1.4 Music Library & Search

- 1.4.1 Build song/artist database

- 1.4.2 Implement song search

- 1.4.3 Implement artist search

- 1.4.4 Display song and artist information

-1.5 Recommendation System

- 1.5.1 Collect user listening preferences

- 1.5.2 Identify similar songs and artists

- 1.5.3 Generate personalized recommendations

- 1.5.4 Add "change my algorithm" recommendations

-1.6 Music Playback

- 1.6.1 Implement audio player

- 1.6.2 Add play/pause controls

- 1.6.3 Add queue functionality

- 1.6.4 Track listening history

-1.7 Playlist System

- 1.7.1 Create playlists

- 1.7.2 Add/remove songs

- 1.7.3 Save playlists

- 1.7.4 Generate recommended playlists

-1.8 Testing

- 1.8.1 Test user accounts

- 1.8.2 Test music search/playback

- 1.8.3 Test recommendation system

- 1.8.4 Fix identified bugs

-1.9 Deployment

- 1.9.1 Prepare production build

- 1.9.2 Deploy application

- 1.9.3 Perform final system testing

- 1.9.4 Release application

- Draft Timeline

| WBS | Activity | Duration | Proposed Weeks |
| --- | --- | --- | --- |
| 1.1 | Project Planning | 2 weeks | 1–2 |
| 1.2 | UI/UX Design | 2 weeks | 2–3 |
| 1.3 | User Account System | 2 weeks | 3–4 |
| 1.4 | Music Library & Search | 3 weeks | 4–6 |
| 1.5 | Recommendation System | 4 weeks | 5–8 |
| 1.6 | Music Playback | 3 weeks | 6–8 |
| 1.7 | Playlist System | 2 weeks | 8–9 |
| 1.8 | Testing & Bug Fixes | 3 weeks | 9–11 |
| 1.9 | Deployment & Finalization | 2 weeks | 12–13 |

| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Planning | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |
| UI/UX Design |  | ■ | ■ |  |  |  |  |  |  |  |  |  |  |
| User Account System |  |  | ■ | ■ |  |  |  |  |  |  |  |  |  |
| Music Library & Search |  |  |  | ■ | ■ | ■ |  |  |  |  |  |  |  |
| Recommendation System |  |  |  |  | ■ | ■ | ■ | ■ |  |  |  |  |  |
| Music Playback |  |  |  |  |  | ■ | ■ | ■ |  |  |  |  |  |
| Playlist System |  |  |  |  |  |  |  | ■ | ■ |  |  |  |  |
| Testing & Bug Fixes |  |  |  |  |  |  |  |  | ■ | ■ | ■ |  |  |
| Deployment & Finalization |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ |

Homework 4

    - Identifying risks

| Category | Possible risks for your music app |
| --- | --- |
| Technical | Recommendation algorithm gives inaccurate suggestions; music API integration fails; database/server issues; user data/security vulnerabilities |
| Schedule | Algorithm takes longer to develop; API integration delays; testing falls behind schedule; features take longer than estimated |
| Financial | API/service costs exceed budget; cloud hosting costs increase; development tools require paid plans; insufficient funding for future expansion |
| People | Team member becomes unavailable; poor communication between team members; uneven workload distribution; lack of experience with certain technologies |

    - Risk Register

| ID | Risk Description | Probability | Impact | Owner | Response Strategy | Status / Notes |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Recommendation algorithm provides inaccurate song suggestions | Medium | High | Development Team | Test and improve the algorithm using user feedback | Monitoring |
| R2 | Music API integration experiences compatibility issues | Medium | High | Development Team | Test API integration early and research backup APIs | Open |
| R3 | Database or server problems cause app downtime | Low | High | Development Team | Use reliable hosting and regularly back up data | Monitoring |
| R4 | Security vulnerability exposes user information | Low | High | Development Team | Use secure authentication and security testing | Open |
| R5 | Recommendation algorithm takes longer to develop than planned | Medium | High | Project Manager | Set development milestones and monitor progress | Open |
| R6 | Testing falls behind schedule | Medium | Medium | Testing Team | Begin testing early and prioritize important features | Open |
| R7 | Music API costs exceed the project budget | Medium | Medium | Project Manager | Monitor API usage and investigate lower-cost alternatives | Monitoring |
| R8 | Cloud hosting costs increase | Low | Medium | Project Manager | Monitor resource usage and establish spending limits | Open |
| R9 | Team member becomes unavailable | Medium | Medium | Project Manager | Cross-train team members and redistribute tasks | Open |
| R10 | Poor team communication causes delays | Medium | High | Project Manager | Hold regular meetings and use a shared communication platform | Monitoring |

    - Communication Plan

| Communication | Participants | Purpose | Method | Frequency | Responsible Person |
| --- | --- | --- | --- | --- | --- |
| Team Meeting | Project team | Discuss progress, upcoming tasks, and problems | In-person / Teams | Weekly | Project Manager |
| Development Update | Developers & Project Manager | Report progress on app features and recommendation algorithm | Teams / Group Chat | Weekly | Development Team |
| Risk Update | Project team | Discuss new risks and changes to existing risks | Team Meeting | Weekly | Project Manager |
| Testing Report | Developers & Testers | Report bugs and problems found during testing | Shared Document | As needed during testing | Testing Team |
| Stakeholder Update | Stakeholders & Project Manager | Explain overall project progress, accomplishments, and upcoming work | Video / Presentation | Weekly | Project Manager |